## Sheet1
Sno | Module | Feature | Estimated date of Requirements Framing | Estimated date Development | Estimated Date of Testing |  | Validation | Sandeep Testing |  | Completion Date
[5 empty] | Start Date | End Date |  | Start Date | End Date |  | Requirement captured from college | requirement documented | requirements shared | development initiated | release for testing | feedback shared | fixes | validation | fixes | validation | release for sandeep testing | fixes | validation | final deplyment
| College Administration Management | Student Admissions | 2023-10-05 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-06 | 2023-11-13
| College Administration Management | Fee Payment Tracking | 2023-10-07 | 2023-10-27 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-06 | 2023-11-08 | 2023-11-15
| College Administration Management | Employee Management | 2023-10-05 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-06 | 2023-11-13
| College Administration Management | Staff Management | 2023-10-05 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-06 | 2023-11-13
| College Administration Management | Payroll | 2023-10-19 | 2023-11-08 | 2023-11-10 | 2023-11-12 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-25
| College Administration Management | ID Card Issue | 2023-10-05 | 2023-10-25 | 2023-10-27 | 2023-10-30 | 2023-11-01 | 2023-11-03 | 2023-11-06 | 2023-11-13
| College Administration Management | Vendor Management | 2023-10-18 | 2023-11-07 | 2023-11-09 | 2023-11-11 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-24
| College Administration Management | Inventory Management | 2023-10-20 | 2023-11-09 | 2023-11-11 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-27
| College Administration Management | Transportation Management | 2023-10-13 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-08 | 2023-11-10 | 2023-11-12 | 2023-11-20
| College Administration Management | Asset Management | 2023-10-21 | 2023-11-10 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-29
| College Administration Management | Hostel Management | 2023-10-11 | 2023-10-31 | 2023-11-02 | 2023-11-04 | 2023-11-06 | 2023-11-08 | 2023-11-10 | 2023-11-17
| College Administration Management | Receipts and Invoices | 2023-10-23 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-12-01
| College Administration Management | Accounting | 2023-10-23 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-12-01
| College Administration Management | Daily Reports | 2023-10-23 | 2023-11-13 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-12-01
| College Academics Management | Operations | 2023-10-25 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-12-02
| College Academics Management | Placement Cell Management | 2023-10-25 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-12-02
| College Academics Management | Infrastructure | 2023-10-25 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-12-02
| College Academics Management | Faculty, Staff Recruitment & Management | 2023-10-25 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-12-02
| College Academics Management | Student Engagement | 2023-10-25 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-12-02
| College Academics Management | Course Delivery Management | 2023-10-25 | 2023-11-14 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-12-02
| College Academics Management | Leave Management | 2023-10-26 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-04
| College Academics Management | Payroll Management | 2023-10-26 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-04
| College Academics Management | Compliance Management | 2023-10-26 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-04
| College Academics Management | College Notices & Circulars | 2023-10-26 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-04
| College Academics Management | Faculty Management | 2023-10-26 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-04
| College Academics Management | Faculty Workload | 2023-10-26 | 2023-11-15 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-12-04
| College Academics Management | Timetables Management | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Attendance Management | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Student Management | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Schedule Meetings/Conferences | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Visitor Management | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Student Approvals | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Asset Management | 2023-10-27 | 2023-11-16 | 2023-11-18 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-12-05
| College Academics Management | Faculty Trainings | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| College Academics Management | Feedback Management | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| Learning Management | Live Classes | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| Learning Management | Recorded Classes | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| Learning Management | Course Materials | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| Learning Management | Online Exams | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| Learning Management | Student Communities | 2023-10-28 | 2023-11-17 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-06
| Learning Management | Course Curriculum | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Semester Calendar | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Exam Management | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Exam Timetables | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Study Material | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Chat with Faculty | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Exam Results | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | College Library | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Learning Management | Red Flags | 2023-10-30 | 2023-11-20 | 2023-11-22 | 2023-11-24 | 2023-11-27 | 2023-11-29 | 2023-12-01 | 2023-12-08
| Parent Management | Student Results | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09
| Parent Management | Student Daily Attendance | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09
| Parent Management | College Circulars and Notices | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09
| Parent Management | Exam Timetables | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09
| Parent Management | Fee Payments | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09
| Parent Management | Placements Information | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09
| Parent Management | Chat with HoD/Mentor. | 2023-10-31 | 2023-11-21 | 2023-11-23 | 2023-11-25 | 2023-11-28 | 2023-11-30 | 2023-12-02 | 2023-12-09